## Board Meeting
RAG Rating Guide
Red | Red - Action date passed - action not complete
Orange | Orange - Action not on target for completion by agreed/revised date
Yellow | Yellow - Action on target to be completed by agreed/revised date
Green | Green- Action complete
Blue | Blue - Action to be removed and replaced by subsequent action
Meeting | Date Raised / Action Ref | Action | Update | Original Target Date | Revised Target Date | RAG Rating | Lead | Status (Open or Complete)
Board Meeting | 28/05/20 PHW88/2020 Chief Executive's Report | QS to share the Response Plan with IANPHI partners, in support of international learning. | Complete |  |  |  | QS | Complete
Board Meeting | 28/05/2020 PHW89/2020 Implementation Plan/Research & Evaluation | QS summarised the ways in which existing research and evaluation activities aligned to the Plan workstreams, as did the ongoing evaluation plans. SB confirmed that she would forward the evaluation of the original contact tracing function. | Evaluation distributed via email |  |  |  | SB | Complete
Board Meeting | 28/05/2020 PHW90/2020 COVID-19 | RB-W set out the work still underway to populate the digital workforce model and agreed to provide added detail outside the meeting. | Additional information shared with Board members via email w/c 22 June 2020. |  |  |  | RBW | In progress
Board Meeting | 28/05/2020 PHW90/2020 COVID-19 | TC confirmed that the executive would take the opportunity of the Organisational Recovery Programme to redesign the process and to present this to the Audit and Corporate Governance (ACGC) Committee. | Item will be added to a future ACGC agenda. Proposed to close from the Board action log |  |  |  | HB | Complete
Board Meeting | 28/05/2020 PHW90/2020 COVID-19/Enclosed cell settings | SP welcomed the role of the Communicable Disease Surveillance Centre in undertaking a number of studies into Care Home settings; this was important work. QS agreed to discuss these epidemiological studies further outside the meeting. | Not held yet but will be scheduled as soon as possible |  |  |  | QS/StP | In progress
Board Meeting | 28/05/2020 PHW90/2020 COVID-19/Enclosed cell settings | In response to a query from JW, AJ provided further detail on the actions in hand to mitigate against the risks set out in section 3.6 of the report. He referenced the shared risk with health boards and advised that the findings from the evaluation would help inform mitigation. | No further action required. |  |  |  | AJ | Complete
Board Meeting | 28/05/2020 PHW96/2020 Board and Committee Work Plans 2020/21 | HB outlined that the work plan would project forwards to September 2020 and provide oversight of the main items being considered in each for a. The Plan would be circulated to the Board in the next week. | Plan further developed and included in the 25 June 2020 Board papers |  |  |  | HB | Complete
Board Meeting | 30/04/20 PHW60/2020 Novel Coronavirus | In view of Board members’ interest in the transitional arrangements, AJ agreed to produce a separate briefing paper. | Paper in progress |  |  |  | AJ | In progress
Board Meeting | 30/04/20 PHW60/2020 Novel Coronavirus | Closed Settings: JW thanked JA and TC for the update; given the significance of the care home sector, she requested specific reports on this sector for future meetings, together with reports on the prison sector, another significant closed setting. In the latter context, she referenced a recent report from Public Health England on the management of COVID-19 in prisons in England and Wales. QS commented on this report and the proposed communications with Public Health England. | No further action required. |  |  |  | JA / QS | Complete
Board Meeting | 30/04/20 PHW60/2020 Novel Coronavirus | Closed Settings: TC outlined the strategic approach under development; Andrew Jones was engaged in this work and she would ask him to provide a written briefing. TC would also forward a letter to the sector from Frank Atherton and Albert Heaney, setting out how the public health system would support care homes. | Letters distributed to Boartd via email. |  |  |  | AJ / TC | Complete
Action on Hold Due to COVID-19 (As agreed at Board meeting on 26 March 2020)
Board Meeting | 23/01/20 PHW05/2020 Board Action Log | Following the introduction of agenda items featuring the organisation’s Strategic Partners, Board members requested regular updates regarding ongoing work and developments with Strategic Partners, including expected impact. | Action on hold due to COVID-19 | 2020-03-26 | 2020-09-30 | Yellow | HB | Open
Board Meeting | 23/01/20 PHW08/2020 Recruitment Deep Dive | Board members went on to request a summary of the correlation between vacancies and the risk to the success of the organisation, and how this was being managed. HG suggested the translation of this issue into a mission critical action plan, reviewed through Board Assurance Framework discussions at Board. | Action on hold due to COVID-19 | 2020-03-26 | 2020-09-30 | Yellow | PB/HB | Open
Board Meeting | 28/11/19 93/2019 Scheme of Delegation | The Board Secretary to further consider delegation of decisions relating to workforce remuneration. | Will form part of the overall scheme of delegation review work that is underway. Now on hold due to COVID-19 | 2020-03-31 | 2020-09-30 | Yellow | HB | Open
Board Meeting | 28/11/19 93/2019 Scheme of Delegation | In relation to the delegation of oversight of risk, The Board agreed that a schematic ‘infographic’ would be helpful in setting out respective Board/Committee roles and responsibilities. | Action on hold due to COVID-19 | 2020-03-31 | 2020-09-30 | Yellow | HB | Open
Board Meeting | 28/11/19 92/2019 Welsh Language Standards | During 2020, the Board resolved to consider further developments around language and culture | Will form part of the Board Development Programme in 2020/21 | 2020/21 |  | Yellow | MB | Open
Board Meeting | 28/11/19 92/2019 Welsh Language Standards | The Board resolved to consider a strategic options paper on translation services | Options to be developed and taken through Exec Team and reported to Board | 2020-06-30 | 2020-09-30 | Yellow | PB | Open
Board Meeting | 28/11/19 89/2019 Intergrated Performance Report | Board members commented on workforce issues being a factor affecting performance across a number of areas......members agreed to ask Health Education and Improvement Wales to meet with the Board/Committee to explore how its remit would address these shortages | PB & RBW met with HEIW to consider areas for them to invest in and potentially fund. POD Chair and Lead Exec to consider if HEIW should be invited to a POD meeting. Update 23/2/20 - action on hold due to COVID-19 | 2020-02-28 | 2020-09-30 | Yellow | PB | Open
Board Meeting | 25/07/19 37.1 Assessment of progress towards a Healthier Wales | The Board commented on the links with Public Health Wales Strategic Priorities and sought further clarity on the performance measures and outcomes for the next year. JB agreed to produce an additional appendix to the report to reflect this. | Update: This action is ongoing - a briefing paper and action plan will be tabled at the Strategic Priorities Coordination Group in November. The paper will ask for nominations for a task and finish group to map the actions in A Healthier Wales to the strategic priorities. As Strategic Priority Groups finalise their outcomes and impact measures this month, the task and finish group will then explore the best method for incorporating these into the assessment. A further update will be provided to the Board in March 2020 (dependant on the work of the strategic priority groups) | 2019-09-25 | 2020-03-26 | Yellow | JB | Open
Completed actions to be approved by the Board
Completed actions to be approved by the Board