|  |  |  |  | Name of Meeting Board |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Date of Meeting 25 March 2021 |  |  |
|  |  |  |  | Agenda item: 3.3 260321 |  |  |
| 2020/21 Financial Position Month 11 |  |  |  |  |  |  |
| Executive lead: |  | Huw George, Deputy Chief Executive and Executive Defector of Finance and Operations |  |  |  |  |
| Author: |  | Angela Fisher, Deputy Director and Head of Finance Ruth Maddern, Head of Financial Management & Business Partnering Suzanne David, Senior Finance Business Partner |  |  |  |  |
| Approval/Scrutiny route: |  | Huw George, Deputy Chief Executive and Executive Defector of Finance and Operations Business Executive Team – 15 March 2021 |  |  |  |  |
| Purpose |  |  |  |  |  |  |
| The purpose of this report is to outline to the Executive Team and the Board the revenue and capital position for Public Health Wales as at 28th February 2021, which includes the position on COVID-19. |  |  |  |  |  |  |
| Recommendation: |  |  |  |  |  |  |
| APPROVE | CONSIDER |  | RECOMMEND |  | ADOPT | ASSURANCE |
| The Board is asked to consider the following: - A surplus financial position of £21k, along with the assumed allocations, reported at month 11; - A forecast year-end break-even position, which includes the month 12 projections for Covid-19 testing capacity; - Status of the Capital Programme, strategic and discretionary, for 2020/21, and - Balance Sheet, or Statement of Financial Position, which includes the cash balance of £5.943m at month 11. |  |  |  |  |  |  |

- Introduction and Context

The purpose of this report is to outline to the Executive Team and the Board the revenue and capital position for Public Health Wales as at 28th February 2021 (M11). The report is also circulated to the Audit and Corporate Governance Committee. The content of this report is reflected in the Director of Finance commentary that has been submitted to Welsh Government on 11th March 2021 as part of the full financial monitoring return for Month 11.

The following table highlights the performance against the key revenue and capital financial targets.

| Target | Current Month | Year to Date | Year-end Forecast |
| --- | --- | --- | --- |
| Revenue financial target Deficit/(Surplus) | 0 | (21K) | Breakeven |
| Capital financial target | 11.955m | 10.690m | Breakeven |
| Public Sector Payment Policy | 96% | 96.26% | >95% |

The Public Health Wales financial position as at 28th February is a net surplus of £21k. This position includes £41.956m of costs directly related to the COVID-19 response, of which:

- £3.008m has been met from within Public Health Wales budgets to cover the following costs as follows:

  - £1.235m from pay underspends;

  - £1.501m from non-pay reductions in spend and internal investment slippage, and

  - £0.272m from the re-purposing of the investment funding from the National Health Protection Service

- £0.928m has been met from external funding in respect of Genomics sequencing tests of £0.875m and platform validation of £0.053m, with

- £38.020m of additional funding from Welsh Government covering:

  - Pay (Quarters 1 & 2) £2.330m;

  - Testing strategy £31.012m;

  - Genomics sequencing £1.423m;

  - IP5 Laboratory Pay £0.659m;

  - Hot Laboratory, Resilience and improved turnaround times Pay £1.039m;

  - Flu Programme £0.127m;

  - £1.115m Online Testing for STIs;

  - Institute of Clinical Science and Technology PPE guidance £0.125m, and

  - COVID-19 Vaccination Programme £0.190m.

- Overview of Financial Performance at Month 11

  - Financial Performance by Directorate

Table A outlines the Financial Performance by Directorate and the Covid-19 response.

Table A – Overview of Financial Performance by Directorate

| Directorate | Income Variance £000s | Pay Variance £000s | Non Pay Variance £000s | Grand Total £000s |
| --- | --- | --- | --- | --- |
| Central Budgets | -81 | 13 | 1,031 | 963 |
| Population Health | 0 | 0 | 0 | 0 |
| ACE's Hub | 0 | 0 | -0 | 0 |
| Hosted | -0 | 19 | -19 | -0 |
| WHO Collaborating Centre | 0 | -42 | 23 | -19 |
| Board and Corporate | -0 | -20 | -37 | -57 |
| Public Health Services | 739 | 296 | -1,096 | -61 |
| Quality Nursing & Allied Health Professionals | -0 | -57 | -8 | -65 |
| People & Organisational Development | 0 | -25 | -42 | -67 |
| Operations and Finance | -0 | -99 | 11 | -87 |
| Improvement Cymru | 69 | -145 | -42 | -119 |
| Knowledge | -23 | -52 | -81 | -156 |
| Health & Wellbeing | 4 | -269 | -89 | -353 |
| Directorate Total | 708 | -379 | -350 | -21 |
| Covid 19 | -0 | -0 | 0 | 0 |
| COVID19 Total | -0 | -0 | 0 | 0 |
| Grand Total | 708 | -379 | -350 | -21 |

The main variance at Month 11 is within Central budgets. Due to the exceptional need to realign budgets at the midpoint in 2020/21, as a result of the impact of CovID on our operations, the Central Budgets are being used to manage a number of financial risks and opportunities. These include the effects of budget realignments, investment slippage, Digital priority commitments and creditor write back.

2.2 Investments

There has been slippage against investments within Public Health Wales due to delays in the allocation of internal investment funding as a result of COVID-19.

Due to the inability of our Directorates to pursue their original investment plans, £1.189m of month’s 1 – 11 investment slippage has been used to form part of Public Health Wales overall financial commitment to supporting the COVID-19 response. The investment monies have been built into Public Health Wales revised Operational plans and forecast breakeven position.

- Forecast position

3.1 Covid-19

NHS Wales organisations are required to submit a COVID19 monitoring return as part of their Monthly Monitoring Returns to Welsh Government. This captures a forecast for all COVID-19 costs for 2020/21 along with non-delivery of planned savings, planned operational expenditure cost reductions and slippage on planned investments.

Appendix 1 includes the full monitoring return submitted by Public Health Wales on 11 March 2021.  Table B3 within the return specifically relates to COVID-19.  Actual costs have been reported for April 2020 to February 2021 and estimated costs have been included for March 2021.  It has been assumed that Welsh Government will fund the remaining COVID-19 expenditure over and above internal funding already identified.

Table C summarises the operational expenditure and funding source of the Public Health Wales Covid-19 response plan:

Table C – Covid-19 financial forecast at month 11

Actual costs for Antigen testing have been reported for April 2020 through to February 2021.  Samples received to December for testing in Welsh laboratories did not exceeded 50% of the capacity available and therefore the forecast for Q4 was reduced based on the assumption that the current levels of testing in Welsh laboratories will continue.  Estimated costs for March 2021 are based on the following testing numbers:

|  | Mar-20 |
| --- | --- |
| Tests per day | 5,000 |
| Total monthly tests | 155,000 |

The original plan was for Public Health Wales to provide capacity for antibody testing to be undertaken in the IP5 laboratory.  Welsh Government approved a contract with Ortho Clinical Diagnostics for the supply of testing kits to deliver this capacity.  Due to a change in Welsh Government policy on antibody testing Public Health Wales are working with Ortho Clinical Diagnostics to verify and validate the kits for use as antigen testing kits.  No additional costs have been included in the forecast for antibody testing.

3.2 All other Directorates

Following the income and expenditure budget scrutiny process a breakeven position has been forecasted for Public Health Wales.  This includes an assumption that Welsh Government will fund the remaining COVID-19 expenditure over and above internal funding already identified.

There remains a clear finance focus on the response, reactivation of essential services and other priorities to ensure underlying financial balance is maintained within the parameters of the Board approved budget for 2020/21.

- Capital

Public Health Wales capital funding for 2020/21 totals £13.042m, summary of the schemes detailed in Table D.

| Fund | Details | 2020/21 Allocation £000's | YTD Spend 2020/21 £000's |
| --- | --- | --- | --- |
| Discretionary | COVID 19 various | 167 | 165 |
| Discretionary | Screening Mobile upscale - Recovery following COVID-19 | 58 | 58 |
| Discretionary | CSIMS Cervical information system NHAIS replacement | 281 | 245 |
| Discretionary | Contingency | 63 | 0 |
| Discretionary | IT - New laptops/desktops/ replacement | 540 | 85 |
| Discretionary | Retinal Image Management System Optpmize Software Support - DESW | 25 | 0 |
| Discretionary | Replacement of virtual infrastructure at CQ2 | 266 | 67 |
| Discretionary | LINC (£58k re provided from 19/20) | 58 | 58 |
| Discretionary | Screening - Replacement Generators, biopsy chair and DESW fire doors | 40 | 8 |
| Discretionary | Replacement dated lighting systems with LED lighting systems | 27 | 24 |
| Discretionary | Class 1 safety cabinet replacement x 6 (Cardiff x4, Carmarthen x 1, Bangor x 1) | 146 | 0 |
| Discretionary Total |  | 1,672 | 711 |
| Strategic | Cepheid Systems | 718 | 718 |
| Strategic | Eplex | 553 | 553 |
| Strategic | PerkinElmer Platforms & Reagents | 740 | 740 |
| Strategic | Hot Labs & Laboratory Resilience | 2,393 | 1,731 |
| Strategic | MAST 3 x Microlab Startlet, optical Unit and thermal cylinder | 429 | 429 |
| Strategic | Imperial Park 5 | 3,989 | 4,671 |
| Strategic | Imperial Park 5 - contingency | 803 | 0 |
| Strategic | MAST Seegene | 666 | 666 |
| Strategic | LINC | 632 | 470 |
| Strategic | NextSeq 550 Sequencing System | 447 | 0 |
| Strategic Total |  | 11,370 | 9,979 |
| PHE Grant | PHE funding (income) | -26 | -26 |
| PHE Grant | Additional genome sequencing | 26 | 26 |
| Total Approved Schemes |  | 13,042 | 10,690 |
| Total Schemes (Approved & Unapproved) |  | 13,042 | 10,690 |

Public Health Wales discretionary allocation of £1.672m remains the same as previous years.  Allocation of this to specific programmes was approved by Business Executive Team in July 2020. An updated Capital paper was submitted to the Business Executive on the 15 December 2020, where approval was given for additional capital schemes and which are reflected in the table above.

PHW Strategic allocation for 20/21 of £11.370m is predominantly driven by the response to COVID-19.  Contingency held for IP5 of £0.803m has been approved.

Of the £4.671m YTD capital expenditure for PHW laboratory capacity at Imperial Park 5 £0.713m reflects the spending on the original laboratory built at Imperial Park 5, which has now transferred to DHSC. These costs will be recovered from DHSC.

A grant has been awarded by Public Health England relating to additional genome sequencing during the winter months, £0.026m of which will be used to purchase capital items.

- Balance Sheet

The Balance Sheet, or Statement of Financial Position, reports the assets, liabilities and reserves of the organisation at a specific point in time. Table E provides a summary as at 28th February 2021.

Table E – Balance Sheet as at 28th February 2021

| ` | Opening Balance 1/4/2020 £000s | Movement £000s | Closing Balance 28/02/21 £000s |
| --- | --- | --- | --- |
| Non-Current Assets |  |  |  |
| Property, plant and equipment | 11,941 | 8,444 | 20,385 |
| Intangible assets | 1,334 | (290) | 1,044 |
| Trade and other receivables | 0 | 240 | 240 |
| Non-Current Assets sub total | 13,275 | 8,394 | 21,669 |
| Current Assets |  |  |  |
| Inventories | 866 | 9,064 | 9,930 |
| Trade and other receivables | 14,379 | 25,356 | 39,735 |
| Cash and cash equivalents | 8,819 | (2,876) | 5,943 |
| Current Assets sub total | 24,064 | 31,544 | 55,608 |
| TOTAL ASSETS | 37,339 | 39,938 | 77,277 |
| Current Liabilities |  |  |  |
| Trade and other payables | (18,898) | (30,891) | (49,789) |
| Provisions | (1,206) | (479) | (1,685) |
| Current Liabilities sub total | (20,104) | (31,370) | (51,474) |
| NET ASSETS LESS CURRENT LIABILITIES | 17,235 | 8,569 | 25,804 |
| Non-Current Liabilities |  |  |  |
| Trade and other payables | (1,381) | (346) | (1,727) |
| Provisions | (1,291) | (224) | (1,515) |
| Non-Current Liabilities sub total | (2,672) | (569) | (3,242) |
| TOTAL ASSETS EMPLOYED | 14,563 | 7,999 | 22,562 |
| FINANCED BY: Taxpayers' Equity |  |  |  |
| PDC | 13,444 | 7,923 | 21,367 |
| Retained earnings | 609 | 19 | 629 |
| Revaluation reserve | 510 | 57 | 567 |
| TOTAL TAXPAYERS' EQUITY | 14,563 | 7,999 | 22,562 |

Non-Current Assets

Property, plant and equipment has increased overall by £8.394m, the majority of which relates to Covid-19 projects.  This reflects the net position of our capital purchases to month 11.

Current Assets

Stock has increased by £9.064m due to purchases of Covid-19 testing consumables for laboratories.  We expect the stock balance to continue to decrease over the coming months as testing progresses.

Trade and other receivables has increased by £25.356m. This increase is predominantly on Whole of Government Accounts receivables comprised of Welsh Government Covid-19 funding of £5.517m and core income of £8.860m for March, which is raised a month in advance. NHS Wales Health Collaborative core income allocation of £1.323m and £6.412m for Implementation Group Delivery Plan income related to several NHSWHC programmes.

Current liabilities

Current trade and other payables has increased by £30.891m.  Welsh Government deferred income of £15.527m is included in this balance relating to baseline core income in advance of £14.392m and income of £1.135m for the increase in annual leave accrual raised in advance.  Other significant accruals include £3.753m for various pay and non-pay accruals and £3.795m deferred income both within the NHS Wales Health Collaborative. In addition there is £2.2m for Screening LTA accrued expenditure.

The increase in provisions of £0.703m is primarily due to 3 new clinical negligence cases in June 20/21.  The Trust is only liable for £75k of the increase in provision, the first £25k of payments on each case, with the remainder being reimbursed by the Welsh Risk Pool.

PDC

The Public Dividend Capital (PDC) balance has increased by £7.923m since the beginning of the year. Welsh Government provided upfront PDC to fund the build of the laboratory at Imperial Park, Newport as well as other Covid-related capital purchases.

- Procurement Activity and Supply Chain

The Audit and Corporate Governance Committee are provided with a report on procurement activity in accordance with paragraph 1.2.1 and Schedule 1 of the SFIs.  This includes an explanation of the reasons and circumstances for Single Quotation Action and Single Tender Action along with the further action taken.

As part of the Sampling and Testing activity a Laboratory Rapid Implementation Programme Board was established to track progress on the increased capacity and monitor impact of any supply chain issues.  The Programme Board provide regular updates to Business Executive Team and appropriate escalation to Board as necessary.

Conclusion

The Board is asked to consider the following:

- A surplus financial position of £21k, along with the assumed allocations, reported at month 11;

- A forecast year-end break-even position, which includes the month 12 projections for Covid-19 testing capacity;

- Status of the Capital Programme, strategic and discretionary, for 2020/21, and

- Balance Sheet, or Statement of Financial Position, which includes the cash balance of £5.943m at month 11.