Appendix 1: Strategic Capital

Replacement of Digital Mammography

Between 2011 and 2014, the Trust received approximately £10m in strategic capital funding to enable the Breast Test Wales programme to move into digital mammography.  The funding provided new mammography equipment, necessary enabling works, conversion of mobile units to include Disability Discrimination Act compliance and a Picture Archive Communication System to enable reading, reporting and transfer of images.

The Trust received strategic capital funding of £4.769m in 2021/22 to start the replacement programme with a further £2.657m of approved Strategic capital in 2022/23 and £0.050m in 23/24 to fully replace the equipment with a total value of £7.476m.

National Programmes Schemes – Decarbonisation and Fire

The Abdominal Aortic Aneurysm screening programme was due to replace their fleet of vehicles to electric vehicles during 2021-22 as part of the decarbonisation programme, due to funding constraints this did not take place.  The infrastructure was put in place during 2021-22 and vehicles will be replaced during 2023-24.

Also, work around compartmentation between areas to prevent fire spreading along with work on fire doors will be undertaken across PHW estates during 2023-24.

It was agreed that Welsh Government would fund 70% of the scheme costs with Public Health Wales contributing 30% from discretionary allocation.

Colposcopy & Colonoscopy Imaging

Cervical cancer is the second most common cancer in women under the age of 40 and the Cervical Screening Wales programme reports that regular screening can cut the risk of getting cancer by 75%.  In 2014/15 Public Heath Wales funded the installation of Colposcopy and Colonoscopy Imaging facilities within Heath Boards to support the viewing of samples to detect abnormal cells more easily and quickly.

Upgrade of the Colposcopy Imaging hardware took place in 2022/23 as the old hardware could not be used with the new platform.  Full replacement of Colposcopy and Colonoscopy Imaging will likely take place during 2025/26.

DESW Camera & Van Replacement

Utilisation of fundus camera equipment and the van fleet are both vital to service delivery and continuity of the DESW programme.  The potential impact of clinic cancellation/capacity reduction due to lack of equipment would lead to a further extension of waiting times for participants between screening appointments, possibly leading to harm (sight loss).  This is of particular concern as a result of already extended recall intervals due to the Covid pandemic.

Due to the current age of our existing cameras (5+ years), DESW will need to embark on a life extension / replacement programme of the current equipment to ensure that the service is able to continue to deliver the service, assuring clinical and quality standards and avoid the need to cancel clinics in the event of any camera failure.  Deployment of new cameras and spare camera backs would be implemented in all 3 regions to minimise down-time by reducing the travel period for camera investigation and swap in the event of equipment failure.  The availability of up to date and spare equipment further reduces lost clinic time by enabling a robust schedule of annual service and cleaning, supporting the delivery of a technical failure rate below NSC guidelines and minimising the need for participant recall due to insufficient quality images.

The DESW van fleet further supports the provision of the screening programme across all regions of Wales, enabling an equitable service delivery.  Again, due to the age of our existing fleet (a number of vans are 8+ years), vehicle replacement enables DESW to meet our legislative requirement for the health and safety of our workforce.  The current cost for the vehicles to remain on the road is beginning to increase and a need for the programme to comply with future emission levels all mean that future fleet replacement will need to be a consideration within the next five years.

Equipment Replacement

Various Screening and Microbiology equipment that falls due for replacement based on a review of our asset register.

10-year Infrastructure Plan Revised  – Estates & Digital